## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Himani | 2025-09-29 | Merged dataset ingestion fails when path is incorrect or files are not mounted in Colab; notebook expects '/content/drive/MyDrive/merged_dataset.csv'. | Sprint 1 - Data Prep | Himani | Data/Environment | Add Drive mount check, validate path using file explorer and add fallback upload option; update notebook documentation. | 2025-09-30 | Closed | User must replace DATA_PATH with actual copied path from Colab sidebar.
2 | Ahibruth | 2025-10-06 | OCR extraction inconsistent on low-quality AADHAR images; Tesseract results noisy in baseline Colab implementation. | Sprint 1 - Data Prep | Ahibruth | Functional/Accuracy | Propose: use Azure Form Recognizer or pre-process images (deskew, denoise) and test on sample images. | 2025-10-07 | Closed | Recommend adding sample preprocessing cell in Colab and using Azure Form Recognizer for production.
3 | Ishan | 2025-10-13 | NLP fine-tuning cell in Colab lacks data split and evaluation metrics logging; risk of overfitting and unverifiable results. | Sprint 2 - Modeling | Ishan | Process/Quality | Update notebook to include train/val/test split, use transformers Trainer or Azure fine-tune with evaluation metrics and model checkpointing. | 2025-10-14 | Closed | Link to notebooks reviewed; need to add explicit metric cells (precision/recall/F1).
4 | Chaitanya | 2025-10-20 | GNN training pipeline in Colab uses in-memory graph construction without batching, causing memory issues on large merged dataset. | Sprint 2 - Modeling | Chaitanya | Performance/Scalability | Refactor DGL graph building to use mini-batching (GraphSAGE) and graph sampling; add memory checks and smaller example dataset. | 2025-10-21 | Closed | Recommend moving heavy training to a VM with more RAM or Azure GPU instance.
5 | Rajeshwari | 2025-10-23 | KYC verification dashboard UI was misaligned, with overlapping fields and missing input validation for AADHAR and address forms | Sprint 3 - Integration | Rajeshwari | UI/UX | Improved the UI layout of the KYC verification dashboard for better readability — fixed alignment of form fields | 2025-10-24 | Closed | Frontend now fully responsive and user-friendly; all input validation messages appear correctly across devices.
6 | Siya | 2025-10-27 | API integration endpoint for real-time verification not present in Colab; need FastAPI wrapper and sample payload tests. | Sprint 3 - Integration | Siya | Integration/Functional | Create FastAPI scaffold with /verify endpoint, wrap saved models, and add sample curl/postman tests in repository. | 2025-10-28 | Closed | Ensure models saved with version metadata and preprocessing functions exported.
7 | Swarada | 2025-11-03 | Deployment checklist missing security and compliance items for handling AADHAR data (PII storage, encryption, legal approvals). | Sprint 4 - Deployment | Swarada | Security/Compliance | Add compliance checklist: data encryption at rest/in transit, RBAC, audit logs, data minimization, and legal sign-off for AADHAR processing. | 2025-11-04 | Closed | Critical before any production deployment; consult legal team for AADHAR handling permissions.
8 | Srujana | 2025-11-07 | During deployment to the Azure sandbox, the AI verification API failed to connect to the database due to incorrect environment variable configuration | Sprint 4 - Deployment | Srujana | Configuration/Deployment | Updated .env configuration with correct database credentials, enabled SSL/TLS for secure connections, and verified deployment through API health checks. | 2025-11-08 | Closed | Deployment now stable and secure; API connects successfully to the database with proper encryption and environment configuration.